## Risk Register
Project |  | CIT
Project Manager |  | Ed Ampuero
Next Business Milestone |  | Feasibility Build Complete (PRS Signed off, incl. TMs)
Target Date |  | 2018-04-23
[9 empty] | Initial |  |  | Residual
Risk Number | Date Initiated | Risk Description | Risk Type | Originator | Risk Owner | First Milestone Impacted | Phase Duration Change | Phase Cost Change | Initial Probability | Phase Duration Change (Weighted) | Phase Cost Change (Weighted) | Mitigated Probability | Phase Duration Change (Weighted) | Phase Cost Change (Weighted) | Proposed Mitigation | Mitigation Owner | Cost of Actions ($) (Difference to Budget) | Mitigation Target Date | Current Mitigation Status | Comments
[9 empty] | <5% = 1 >5%<25% = 3 >25% = 9 |  |  | <5% = 1 >5%<25% = 3 >25% = 9 | [8 empty] | Risk Types
1 | 2018-03-01 | Device design to achieve cost target makes it difficult to disinfect/resterilize | Sterilization/Biocomp Risk | Ed | Alex | Feasibility Verification Testing Complete | 3 | 340000 | 3 | 2.25 | 170000 | 3 | 2.25 | 170000 | [5 empty] | Updated probability to reflect endoscope design | Design Risk
2 | 2018-03-01 | Leadtime/availability of optical components resulting in delay | Supplier Risk | Ed | Ed | Feasibility Verification Testing Complete | 3 | 25000 | 9 | 3 | 25000 | 9 | 3 | 25000 | None Approved: - Determine alternate test configurations to proceed without full camera components. - Consider alternate vendor | Ed |  | 2018-08-30 | Tracking | Shifted to Feasibility Verification Testing. Camera was off-scoped from Proof of Concept Phase | Regulatory Risk
3 | 2018-03-01 | Device design to achieve cost target not aligned with previous IP assessment | IP Risk | Ed | Ed | End of Proof of Concept Phase (TMs drafted) | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | Design reviews with IP advisor scheduled as needed |  |  |  |  | Removed risk, was 3 months/$225k. Proof of Concept COGS Assessment inline with targets | Supplier Risk
4 | 2018-03-01 | Optical vendor not qualified for long term production resulting in new vendor at Transfer Phase | Supplier Risk | Ed | Ed | Complete Transfer Phase | 4 | 220000 | 3 | 3 | 110000 | 3 | 3 | 110000 | Request new SOW from camera vendor and mid-May deliverable | Ed |  | 2018-05-25 | Tracking |  | IP Risk
5 | 2018-03-01 | Water ingress design iterations require additional quantity and duration | Design Risk | Alex | Alex | Feasibility Verification Testing Complete | 3 | 225000 | 3 | 2.25 | 112500 | 3 | 2.25 | 112500 | [5 empty] | Shifted to Feasibility Verification Testing. | Production Risk
6 | 2018-03-01 | Availability of manufacturing equipment resulting in schedule delay | Supplier Risk | Ed | Ed | Feasibility Verification Testing Complete | 2 | 20000 | 1 | 1 | 2000 | 1 | 1 | 2000 | Identify manufacturing partners with needed capabilities | Duane | 0 | 2018-05-11 | Tracking | Shifted to Feasibility Verification Testing. | Sterilization/Biocomp Risk
7 | 2018-03-01 | Negative validation results at client cause changes to DI | Scope Creep Risk | Ed | Ed | End of Design & Development Phase | 6 | 2239800 | 3 | 4.5 | 1119900 | 3 | 4.5 | 1119900 | [6 empty] | Manufacturing Move/Transfer Risk
8 | 2018-03-01 | Planned production partner not willing to accept product due to significant electronics/optical component | Production Risk | Ed | Ed | Complete Transfer Phase | 3 | 330000 | 9 | 3 | 330000 | 3 | 2.25 | 165000 | Identify new production partner | Ed | 0 | 2018-03-01 | Tracking |  | Execution Risk
9 | 2018-03-05 | Sample size for DV less than budgeted | Execution Risk | Ed | Ed | End of Design & Development Phase | 0 | -840000 | 1 | 0 | -84000 | 1 | 0 | -84000 | [6 empty] | Reimbursement Risk
10 | 2018-04-23 | Optical vendor requires additional NRE to achieve design targers | Supplier Risk | Ed | Ed | Feasibility Verification Testing Complete | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | [6 empty] | Scope Creep Risk
11 | 2018-07-16 | Camera look-down angle not adequate resulting in need for tilt-down feature at camera vertebrae | Design Risk | Ed | Ed | End of Design & Development Phase | 3 | 225000 | 9 | 3 | 225000 | 9 | 3 | 225000 | None Approved: Initiate Design Activity | Ed | 45000 | 2019-01-04 | Not Approved | Cost assumes 2 months of Design Workforce at 50% | Test Method Development Risk
12 |  | Accelerated DV schedule required portion of DV to be repeated prior to end of Phase II |  |  |  | End of Design & Development Phase | 2 | 375000 | 9 | 2 | 375000 | 9 | 2 | 375000
13 |  | Design challenges associated with selectively-compliant endoscope shaft not fully captured, resulting in additional development efforts |  |  |  | End of Design & Development Phase | 3 | 225000 | 9 | 3 | 225000 | 3 | 2.25 | 112500
Crystal Ball -> |  | Duration: Max value of all weighted scores - Assumes 100% of 9's - Assumes 75% of 3's - Assumes 50% of 1's Cost: Sum of all weighted scores - Assume 100% of 9's - Assume 50% of 3's - Assume 10% of 1's | [6 empty] | Initial | 4.5 | 2440400 | Residual | 4.5 | 2162900